## Slide 1
PROJECT DELIVERY BRIEF
PM Under Pressure
Delivery Plan — CloudMetrics Dashboard Project
2 Devs
Team Size
20 Days
Capacity
26 Days
Work Needed
Presented by: Harsh

## Slide 2
Situation Overview
Client Request
The client expects 5 features to be fully built and delivered within just 2 weeks. This is a tight deadline with a small team.
Team Capacity
We have 2 developers available, giving us a total of 20 developer-days. Every day matters and must be used wisely.
Actual Work Required
After detailed estimation, completing all 5 features properly requires 26 developer-days. That's 6 days more than we have.
The Core Problem
Delivering everything at once is not realistic without cutting quality or skipping testing — both of which create serious risks in production.

## Slide 3
Our Approach
01
Focus on What Matters Most
We identified the features that deliver the highest value to users. By focusing on essentials first, we make sure the product actually works well for the board meeting.
02
Deliver a Stable, Usable Product
A product that works reliably is far better than one with more features but bugs. We include proper testing time to make sure nothing breaks in production.
03
Avoid High-Risk Features
Features that are too large or complex create unpredictable delays. We move those to Phase 2 so they don't jeopardize the entire delivery.
04
Leave Room for Quality Checks
We've built a 3-day buffer into the plan for integration, bug fixes, and last-minute adjustments. This is not waste — it's what separates good delivery from great delivery.

## Slide 4
Features We Will Deliver
A
Real-Time Alert Dashboard
6 Days
• Displays live alerts by severity so the team can monitor system health at a glance.
• Includes filters, acknowledgment buttons, and real-time state updates for fast action.
D
Email + Slack Notifications
3 Days
• Automatically sends alerts via email and Slack when thresholds are breached.
• Keeps the team informed without them needing to stare at a dashboard all day.
B
Historical Trend Charts
5 Days
• Shows CPU, memory, and disk usage over time with flexible time range selectors.
• Lets the team spot patterns and plan capacity — great for impressing stakeholders in the demo.
C
Access Control (MVP Only)
4 Days
• Delivers team-level access control so different groups see only their assigned services.
• Full role hierarchy is scoped for Phase 2; this MVP version covers the critical need now.

## Slide 5
Features Deferred to Phase 2
E
Custom Report Builder
9 Days Work
This feature alone needs 9 developer-days — nearly half our entire capacity. It includes a drag-and-drop builder, PDF export, a scheduling engine, and a complex backend pipeline.
Including it now would delay all other critical features and introduce high architectural risk before the board meeting.
Too Large to Fit
At 9 days, it doesn't fit within our 20-day budget once critical features are accounted for. There's simply no safe room.
High Architectural Risk
The report engine and scheduler require new systems that could destabilize the whole app if rushed without proper design.
Not Needed for Demo
The board meeting demo doesn't require reports. Delivering it in Phase 2 means it gets built properly, not hastily.

## Slide 6
Delivery Plan — 20 Developer Days
Chart: 
| Days
Feature A Alert Dashboard | 6
Feature D Notifications | 3
Feature B Trend Charts | 5
Feature C Access Control (MVP) | 4
Integration Buffer | 8
Sprint Breakdown
Feature A — Alert Dashboard
6d
Feature D — Notifications
3d
Feature B — Trend Charts
5d
Feature C — Access Control (MVP)
4d
Integration Buffer
8d
TOTAL: 26 / 20 Days Used
1 day remaining as final contingency buffer.

## Slide 7
Why This Plan Works
Complete and Usable Product
Every feature we deliver will be fully built, tested, and ready for real use. The client won't receive a half-finished product — they'll get a reliable, working system.
Strong Board Meeting Demo
The selected features — dashboards, alerts, charts, and notifications — are exactly what makes a monitoring platform impressive. The demo will clearly show business value.
Low Risk of Failure
By being realistic about scope, we avoid the most common cause of project failure: overcommitting. Our plan protects both team quality and client trust.
Built-In Quality Buffer
We have 3 days reserved for integration and bug fixes. This means the product gets reviewed, tested, and polished before it goes in front of decision makers.
Phase 2 Already Planned
Deferred features are not forgotten — they are documented and ready to be scheduled immediately after the Phase 1 launch, keeping momentum going.
Honest Client Communication
We're being upfront about what can be done well in the time available. This builds more long-term trust than overpromising and underdelivering.

## Slide 8
Handling Tough Client Questions
Q1: 'Why can't your team just work overtime?'
Overtime doesn't make complex systems simpler. Our delivery involves authentication, data pipelines, and real-time systems — extra hours increase mistakes, not speed. A buggy monitoring platform is worse than a scoped one.
Q2: 'Feature C was our top priority — why deprioritize it?'
We didn't deprioritize it. We're delivering a working MVP of Access Control this sprint — team-level permissions are included. Full role hierarchy (viewer/editor/admin) requires deeper changes that would block everything else.
Q3: 'Our competitor delivered all of this in one week!'
Fast delivery usually means pre-built infrastructure, reduced scope, or lower quality standards. Our plan is built for production-grade reliability, security, and scalability — not just feature surface. We build it once, correctly.
Our focus: Stability · Reliability · Honest Communication

## Slide 9
Thank You!
Questions & Discussion
Key Takeaways
✔ Phase 1 delivers core value — dashboard, alerts, charts, notifications, access control
✔ Custom Report Builder moves to Phase 2 for proper, risk-free development
✔ Our plan prioritises reliability and client trust over feature quantity