## Slide 1
Day 7: Project Management & Decision Making
IOanyT Workshop — Cohort 1
March 25, 2026
IOanyT
Notes: TIMING: 30 seconds
TALKING POINTS:
- Welcome to Day 7! Today you become the PM
- You'll make hard decisions: what ships, what doesn't, how to say "no"
- This tests decision-making under constraints — a critical PM skill
TRANSITIONS:
- "Standup."

## Slide 2
Daily Standup
Daily Standup (9:00-9:15 AM)
Round-robin (2 min each):
• What did you learn from QA/bug hunting yesterday?
• What are you focusing on today?
• Blockers?
IOanyT Workshop
Confidential — Evaluator Copy
Notes: TIMING: 15 minutes
TALKING POINTS:
- Standup
- (Listen for connections between QA and PM — both require systematic thinking)
EVALUATION CUES:
- Who mentions trade-offs from testing?
TRANSITIONS:
- "Agenda."

## Slide 3
Today's Agenda
Morning (9:15 AM - 12:30 PM):
PM Essentials: Estimation & Prioritization (60 min)
Live Demo: RICE Scoring (30 min)
Exercise: Backlog Prioritization (60 min)
Debrief (30 min)
Afternoon (1:30 PM - 5:15 PM):
• **INDIVIDUAL EXERCISE**: PM Under Pressure (120 min)
**INDIVIDUAL PRESENTATIONS** (10 min each + 5 min Q&A)
Reflection (15 min)
Focus: Process & Decision Making (PRIMARY DIMENSION)
⚠️ Afternoon presentations are SCORED ⚠️
IOanyT Workshop
Confidential — Evaluator Copy
Notes: TIMING: 2 minutes
TALKING POINTS:
- Morning: Learn estimation and prioritization frameworks
- Afternoon: Apply under pressure — you're the PM, client wants impossible timeline
- You'll present your decisions to us (playing demanding clients)
- Assessment focus: Process & Decision Making — can you make tough calls and defend them?
TRANSITIONS:
- "Learning objectives."

## Slide 4
Learning Objectives
By the end of Day 7, you will:
✓
Estimate features using T-shirt sizing and story points
✓
Prioritize a backlog using RICE scoring or MoSCoW
✓
Create a realistic delivery plan under constraints
✓
Defend trade-off decisions under pressure
✓
Say "no" gracefully when scope exceeds capacity
IOanyT Workshop
Confidential — Evaluator Copy
Notes: TIMING: 2 minutes
TALKING POINTS:
- Five PM-focused objectives
- Estimation: T-shirt sizing (S/M/L/XL) and story points
- Prioritization: RICE framework (Reach, Impact, Confidence, Effort)
- Delivery planning: Realistic, not fantasy timelines
- Defending decisions: Clients will push back — can you hold your ground?
- Saying no: Hardest PM skill — graceful scope management
TRANSITIONS:
- "Assessment transparency."

## Slide 5
Assessment Transparency
What We're Evaluating Today
Primary Dimension: Process & Decision Making (15% weight)
⚠️ AFTERNOON PRESENTATIONS ARE HEAVILY WEIGHTED ⚠️
What Good Looks Like:
✓ Realistic planning (not over-promising)
✓ Clear trade-off reasoning (why X over Y?)
✓ Holding ground under pressure (not caving to demands)
✓ Saying "no" gracefully (not just "yes" to everything)
✓ Systematic approach (using frameworks, not gut feel)
What We're NOT Looking For:
✗ Perfect estimates (estimation is hard, process matters)
✗ Always saying "yes" (pleasing clients ≠ good PM)
Key: Can you make hard decisions and defend them?
IOanyT Workshop
Confidential — Evaluator Copy
Notes: TIMING: 3 minutes
TALKING POINTS:
- Primary dimension today: Process & Decision Making
- Afternoon presentations are MAJOR signal — we'll play demanding clients
- Good looks like: Realistic planning. "We can do 3 features in 2 weeks, not 5." That's honesty
- Clear reasoning. "I prioritized Feature A over Feature B because: (business impact, risk, dependencies)"
- Holding ground. When we push back ("Can't you just work weekends?"), can you say no professionally?
- Graceful "no": "I understand this is important, AND here's what's possible given constraints"
- We're NOT expecting perfect estimates. Estimation is hard. What matters: Did you use a systematic approach?
- Bad PM always says yes, delivers nothing. Good PM says no when needed, delivers quality
FACILITATION TIPS:
- Set expectations: "We WILL pressure you this afternoon. That's the test"
TRANSITIONS:
- "PM essentials."

## Slide 6
Estimation Approaches
How to Estimate (When You Don't Know How Long Things Take)
3 Approaches:
1. T-SHIRT SIZING (Relative)
S (small), M (medium), L (large), XL (extra-large)
Compare to known features
2. STORY POINTS (Fibonacci)
1, 2, 3, 5, 8, 13, 21 (bigger = more uncertain)
Relative complexity, not hours
3. TIME-BASED (Risky)
"This will take 2 days"
Often wrong, but sometimes needed
Best Practice at IOanyT:
Start with T-shirt, refine to story points, avoid time-based until late
IOanyT Workshop
Confidential — Evaluator Copy
Notes: TIMING: 10 minutes
TALKING POINTS:
- Estimation is HARD. Even senior engineers get it wrong
- Three approaches (show slide)
- T-shirt sizing: Simplest. "This feature is Medium compared to that Small feature"
- Example: Login page (S), Dashboard (M), Analytics (L), Full e-commerce (XL)
- Why it works: Relative comparison is easier than absolute estimation
- Story points: More granular. Fibonacci sequence (1, 2, 3, 5, 8, 13...)
- Why Fibonacci? Gap increases as uncertainty increases. 13-point story is WAY more uncertain than 8-point
- Story points combine complexity, risk, and effort (not just time)
- Time-based: "This is 2 days of work." Dangerous because:
- Assumes no blockers
- Assumes you know the problem fully
- Doesn't account for unknowns
- Use time-based only when forced to by client
- IOanyT best practice: Start with T-shirt to get rough sizing. Refine to story points. Avoid committing to hours until late
- AI can help estimate, but YOU apply judgment: "Claude says 3 points, but our codebase is legacy, so actually 5 points"
FACILITATION TIPS:
- Poll: "Who's estimated software before?" (Invite 1-2 to share war stories of missed estimates)
EVALUATION CUES:
- Who asks "How do you account for unknowns?"
TRANSITIONS:
- "Estimation is input. Prioritization is output."

## Slide 7
Prioritization Frameworks
How to Decide What to Build First
RICE SCORING (IOanyT Default):
R = REACH (how many users affected?)
I = IMPACT (how much impact per user? 0.25-3x)
C = CONFIDENCE (how confident are we? 0%-100%)
E = EFFORT (how much work? person-months)
RICE Score = (R × I × C) / E
Example:
Feature A: (1000 users × 2x impact × 80% confidence) / 2 months = 800
Feature B: (500 users × 3x impact × 50% confidence) / 1 month = 750
Feature A wins (higher score)
Alternative: MoSCoW (Must, Should, Could, Won't)
IOanyT Workshop
Confidential — Evaluator Copy
Notes: TIMING: 12 minutes
TALKING POINTS:
- Prioritization: You have 10 features, time for 3. How do you choose?
- RICE framework (IOanyT standard)
- Reach: How many users? 100? 10,000? All users?
- Impact: Per user, how much impact? Massive (3x), High (2x), Medium (1x), Low (0.5x), Minimal (0.25x)
- Confidence: How confident in your estimates? 100% (we've built this before), 80% (pretty sure), 50% (guessing)
- Effort: Person-months. 1 dev-month? 6 dev-months?
- Formula: (Reach × Impact × Confidence) / Effort
- Higher score = higher priority
- Example (walk through slide): Feature A scores 800, Feature B scores 750. Feature A wins
- Why this works: Forces you to think about value (reach × impact) vs cost (effort). Confidence adjusts for uncertainty
- Alternative: MoSCoW (Must have, Should have, Could have, Won't have). Simpler, less quantitative
- When to use MoSCoW: Early stages, stakeholder alignment
- When to use RICE: Detailed planning, multiple competing features
- AI can help calculate RICE, but YOU provide the numbers (reach, impact, confidence, effort)
FACILITATION TIPS:
- Walk through RICE calculation on whiteboard with different examples
EVALUATION CUES:
- Who asks "What if confidence is 0%?" (Answer: Don't build it, or spike first)
TRANSITIONS:
- "Let me show you RICE in action."

## Slide 8
Live Demo — RICE Scoring
Live Demo: Prioritize 5 Features Using RICE
Scenario: Client wants all 5 features, you have time for 2.
Features:
1. User authentication
2. Search functionality
3. Email notifications
4. Analytics dashboard
5. Mobile app
Watch me:
1. Estimate Reach, Impact, Confidence, Effort for each
2. Calculate RICE scores
3. Prioritize based on scores
4. Explain trade-offs (why top 2, not others)
IOanyT Workshop
Confidential — Evaluator Copy
Notes: TIMING: 30 minutes (10 min setup + 20 min demo)
TALKING POINTS:
- Live demo: RICE scoring on 5 competing features
- Scenario (read from slide): Client wants all, you have capacity for 2
- Let's estimate each feature
- Feature 1: User authentication
- Reach: 100% of users (1000)
- Impact: 3x (must-have for app to work)
- Confidence: 80% (we've built this before)
- Effort: 1 person-month
- RICE: (1000 × 3 × 0.8) / 1 = 2400
- Feature 2: Search
- Reach: 80% of users (800)
- Impact: 2x (high value)
- Confidence: 60% (complex feature, unknowns)
- Effort: 2 person-months
- RICE: (800 × 2 × 0.6) / 2 = 480
- (Continue through all 5 features, calculate RICE for each)
- Final ranking: Auth (2400), Notifications (800), Search (480), Analytics (300), Mobile (200)
- Decision: Build Auth + Notifications (top 2 by RICE)
- Trade-offs: Why not Search (lower RICE, higher effort, more uncertainty). Why not Mobile (lowest score, huge effort)
- If client pushes back: "Mobile is strategic!" → Response: "I understand. Given current capacity, would you prefer Mobile over Auth? That means no login for 2 months. Is that acceptable?"
- This is PM work: Data-driven decisions + communication
FACILITATION TIPS:
- Show the calculations visibly (spreadsheet or whiteboard)
- Demonstrate the client pushback conversation
EVALUATION CUES:
- Who's taking notes on RICE numbers?
TRANSITIONS:
- "Your turn to prioritize."

## Slide 9
⚡
Morning Exercise — Backlog Prioritization
Exercise: Backlog Prioritization (Individual)
Objective: Prioritize 15 features for a 2-week sprint
Time: 60 minutes
Format: Individual
Setup: Feature backlog in /day-7/backlog.md (15 items)
Your Task:
1. For each feature, estimate: Reach, Impact, Confidence, Effort
2. Calculate RICE scores (use spreadsheet template)
3. Prioritize: What fits in 2-week sprint? (assume 2 devs)
4. Document reasoning in PRIORITIZATION.md
Deliverable:
• Completed RICE spreadsheet
• PRIORITIZATION.md (what's in, what's out, why)
IOanyT Workshop
Confidential — Evaluator Copy
Notes: TIMING: 5 minutes setup
TALKING POINTS:
- Practice prioritization
- You have 15 features (in /day-7/backlog.md)
- 2-week sprint, 2 developers (assume ~4 person-weeks capacity)
- Your job: Estimate RICE for each, prioritize, decide what fits
- Step 1: For each feature, estimate Reach, Impact, Confidence, Effort
- Step 2: Calculate RICE (use spreadsheet template, or ask Claude to calculate)
- Step 3: Rank by RICE score
- Step 4: Decide what fits in sprint capacity
- Step 5: Document in PRIORITIZATION.md: What's in? What's out? Why?
- Deliverable: Two files (RICE spreadsheet + reasoning doc)
- 60 minutes. Be systematic
FACILITATION TIPS:
- Provide spreadsheet template for RICE calculations
- Circulate and observe
EVALUATION CUES:
- Who uses RICE systematically vs gut feel?
- Quality of trade-off reasoning
TRANSITIONS:
- "60 minutes. Go!"

## Slide 10
Morning Debrief
What Did You Prioritize?
Discussion (30 min):
• What features did you prioritize (top 3)?
• What trade-offs did you make?
• Did anyone's prioritization differ significantly? Why?
• How did you handle uncertainty (low confidence)?
Show of hands:
• Who prioritized differently than RICE suggested? Why?
• Who found this harder than expected?
• Who's ready for this afternoon's pressure test?
IOanyT Workshop
Confidential — Evaluator Copy
Notes: TIMING: 30 minutes
TALKING POINTS:
- Debrief. What did you prioritize?
- (Invite 5-7 candidates to share their top 3)
- Interesting question: Did everyone prioritize the same features?
- If yes: RICE is working (data-driven consensus)
- If no: What drove the differences? (Different estimates? Different interpretations?)
- Trade-offs: What did you CUT? That's the hard part
- Handling uncertainty: If confidence was 20%, what did you do? (Options: Don't build it. Spike to increase confidence. Build anyway but flag risk)
- Show of hands (ask questions from slide)
- If someone prioritized against RICE: "Why did you override the score?" (Sometimes qualitative factors matter — that's judgment)
- Key learning: Framework gives you DATA, YOU make the DECISION
FACILITATION TIPS:
- Celebrate different approaches: "Both are valid if reasoning is sound"
EVALUATION CUES:
- Quality of reasoning when overriding RICE
TRANSITIONS:
- "Lunch break. This afternoon: PM under pressure."

## Slide 11
⚡
Afternoon Exercise — PM Under Pressure
INDIVIDUAL EXERCISE: PM Under Pressure
⚠️ THIS IS A SCORED PRESENTATION ⚠️
Time: 120 minutes prep + 15 min presentation each
Format: Individual
Scenario:
Client wants 5 features in 2 weeks.
Budget: Fixed.
Team: 2 developers.
Timeline: Non-negotiable (product launch tied to conference).
The 5 features total 6 person-weeks (you have 4).
Your Task:
1. Estimate each feature using Claude (30 min)
2. Create realistic delivery plan using RICE (40 min)
3. Decide: What's in? What's out? What's at risk? (30 min)
4. Prepare 10-minute presentation defending decisions (20 min)
Deliverable: DELIVERY-PLAN.md + 10-min presentation
IOanyT Workshop
Confidential — Evaluator Copy
Notes: TIMING: 7 minutes setup
TALKING POINTS:
- This is the afternoon assessment. High pressure, just like real PM work
- Scenario (read from slide): Client wants 5 features, 2 weeks, 2 devs
- The catch: Features total 6 person-weeks. You have 4. Math doesn't work
- This is REALITY. Clients always want more than capacity allows
- Your task (point to slide):
- Estimate each feature (use Claude to help, but you validate)
- Use RICE to prioritize
- Create delivery plan: What's IN (definitely building), What's OUT (definitely not), What's AT RISK (maybe, if time)
- Prepare 10-minute presentation to the "client" (us, the evaluators)
- You have 120 minutes to prep
- Then, each of you will present (10 min) + face tough Q&A (5 min)
- What we're evaluating:
- Is your plan REALISTIC? (Not fantasy: "We'll work weekends")
- Is your reasoning CLEAR? (Why Feature A over Feature B?)
- Can you DEFEND under pressure? (When we push back, do you cave or hold ground?)
- Can you say NO gracefully? (We'll ask for all 5 features. Can you say no professionally?)
- Scenario details in /day-7/pm-scenario.md
- Questions before we start?
FACILITATION TIPS:
- Provide scenario with 5 features (detailed specs, so they can estimate)
- Set visible 120-minute timer
- Emphasize: "This is realistic. You'll face this at IOanyT"
EVALUATION CUES:
- (This is primary assessment)
- Realism of plan
- Clarity of reasoning
- Response to pressure
TRANSITIONS:
- "120 minutes prep starts now."

## Slide 12
Individual Presentations
Individual Presentations (15 min each)
Format:
• 10 minutes: Present your delivery plan
• 5 minutes: Tough Q&A from evaluators
What to cover:
• Your RICE scores and prioritization
• What's in scope, what's out, what's at risk
• WHY (trade-off reasoning)
• Mitigation for risks
Evaluator Questions (Examples):
• "Why did you cut Feature X? It's critical!"
• "Can't you just add one more developer?"
• "What if we pay overtime for weekends?"
• "Your competitor promised all 5 features in 2 weeks."
IOanyT Workshop
Confidential — Evaluator Copy
Notes: TIMING: 180 minutes total (12 candidates × 15 min = 180 min = 3 hours)
TALKING POINTS:
- Presentation time! Each candidate gets 15 minutes (10 present + 5 Q&A)
- We'll go in order (call candidates by name)
- Present your delivery plan: RICE scores, prioritization, what's in/out/at-risk, reasoning
- Then we'll grill you. We're playing demanding clients
- Example questions (show slide): These are REAL questions you'll face at IOanyT
- (After each presentation):
- "Why did you cut Feature X? Client says it's critical!" (Test: Can they defend decision with data?)
- "Can't you just add one more developer?" (Test: Do they know adding people slows projects initially?)
- "What if we pay overtime for weekends?" (Test: Will they cave to unhealthy practices?)
- "Competitor promised all 5 in 2 weeks." (Test: Can they call out unrealistic promises?)
- What we're looking for:
- Calm under pressure
- Data-backed reasoning
- Professional "no": "I understand this matters, AND here's what's possible given constraints"
- Not caving: Sticking to realistic plan even when pressured
- (After all presentations): Debrief common patterns
FACILITATION TIPS:
- Keep presentations to 10 min (use timer)
- Ask genuinely tough questions (not gotchas, but realistic pressure)
- Vary questions per candidate (don't ask same question to everyone)
- Note who holds ground vs who caves
EVALUATION CUES:
- Plan realism (did they over-promise?)
- Reasoning clarity (can they explain trade-offs?)
- Pressure response (do they cave or hold?)
- Graceful "no" (professional boundary-setting)
TRANSITIONS:
- "Excellent work under pressure. Resources."

## Slide 13
Resources for Day 7
Resources for Day 7
📚 Reading:
• "The Mythical Man-Month" (Brooks) — excerpts on estimation
• RICE framework deep-dive
💡 Examples:
• Real IOanyT delivery plans (sanitized)
• Prioritization case studies
📝 Templates:
• RICE-scoring-template.xlsx
• DELIVERY-PLAN-template.md
🔧 Tools:
• Google Sheets for RICE calculations
All in /day-7/
IOanyT Workshop
Confidential — Evaluator Copy
Notes: TIMING: 1 minute
TALKING POINTS:
- Resources in /day-7/
- "Mythical Man-Month" is classic (adding people to late project makes it later)
- RICE template reusable for real projects
TRANSITIONS:
- "Reflection."

## Slide 14
Closing — Daily Reflection
Wrapping Up Day 7
Daily Reflection (2 min):
→ One thing you learned about PM decision-making
→ One decision you're proud you defended
Tomorrow Preview:
📅 Day 8: Full-Stack AI Orchestration
Focus: Collaboration + Adaptability
You'll work across multiple AI-assisted roles (PM, BA, Eng, QA) and practice role-switching.
Less pressure tomorrow, more skill-building.
See you at 9:00 AM! 🚀
Notes: TIMING: 5 minutes
TALKING POINTS:
- Day 7 complete! Toughest day yet (pressure presentations)
- You survived demanding clients — that's real PM work
- Reflect (2 min silence)
- Tomorrow: Day 8 is multi-role orchestration. You'll rotate through PM, BA, Eng, QA roles
- Less pressure, more collaboration practice
- Submit DELIVERY-PLAN.md if you haven't
- Well done today!
FACILITATION TIPS:
- Acknowledge effort: "That was intense. You handled it well"
EVALUATION CUES:
- (Score presentations tonight — realism, reasoning, pressure response)
TRANSITIONS:
- "Day 7 done!"