## ComplianceOG
Category | Requirement | Expected | Actual | Status | Comments
Handoff | Working API | Endpoints accessible and runnable | Basic weather fetch may work | Pass | Assumed runnable from project handoff
Handoff | Documentation | Clear setup and usage documentation | Available separately | Partial | Needs alignment to BA-specific behavior
BA Compliance | Fetch Weather by City | GET /api/v1/weather?city={city} returns current weather + 3-day forecast | Core fetch likely implemented | Pass/Partial | Need validation against exact schema
BA Compliance | City Validation | City required, 2-100 chars after trim, allowed chars only | Generic validation likely partial | Partial | Need strict regex/length validation
BA Compliance | City Normalization | Trim, collapse spaces, lowercase for cache key | Not confirmed | Fail | Must support deterministic cache key
BA Compliance | Current Weather Schema | Return cityName, countryCode, observationTimeUtc, temperatureC, condition, humidityPercent, windSpeedKph | May return provider/raw structure | Partial | Needs canonical schema mapping
BA Compliance | 3-Day Forecast Schema | Return exactly 3 forecast day entries when available | Not confirmed | Partial | Often missed or variable-length only
BA Compliance | Forecast Partial Metadata | If fewer than 3 days, set metadata.forecastCompleteness=partial | Not confirmed | Fail | BA explicitly requires fallback rule
BA Compliance | Cache Lookup | Check cache before external provider call | Not confirmed | Fail | Core BA requirement
BA Compliance | Cache TTL | Fresh cache valid for 30 minutes | Not confirmed | Fail | TTL behavior required
BA Compliance | Cache Metadata | Response includes cacheHit, cacheTtlSeconds, dataTimestampUtc | Not confirmed | Fail | Response metadata often incomplete
BA Compliance | Stale Fallback | On provider failure and stale cache <= 6 hours, return stale cached data | Not confirmed | Fail | Key resilience requirement
BA Compliance | Dependency Failure | On provider failure and no acceptable cache, return 503 DEPENDENCY_UNAVAILABLE | Not confirmed | Partial | Must be standardized
BA Compliance | Provider Timeout | Configurable timeout default 3 seconds | Not confirmed | Fail | BA/NFR requirement
BA Compliance | Retry Policy | Max 1 retry with backoff for transient failures | Not confirmed | Fail | NFR requirement
BA Compliance | Unknown City Handling | Well-formed unknown city returns 404 CITY_NOT_FOUND | Not confirmed | Partial | Must be deterministic
BA Compliance | Standard Success Schema | Same response structure on cache hit and miss | Not confirmed | Fail | Important for automation stability
BA Compliance | Standard Error Schema | Errors include requestId, code, message, fieldErrors, timestampUtc | Not confirmed | Fail | Common gap
BA Compliance | Health Endpoint | GET /api/v1/health exists | Not confirmed | Fail | Operational requirement
BA Compliance | Metrics Endpoint | GET /api/v1/metrics exists | Not confirmed | Fail | Operational requirement
BA Compliance | Request Logging | Log normalized city, cache result, provider latency, final status, requestId | Not confirmed | Fail | Observability requirement
BA Compliance | Metrics Counters | Expose total requests, cache hits/misses, provider failures, validation failures | Not confirmed | Fail | Required by BA/NFR
Security | Input Sanitization | Reject malformed/injection-like city inputs | Not confirmed | Partial | Needs strict validation
Security | Internal Exposure Only | Endpoint limited to trusted network | MVP assumption only | Partial | Deployment/network concern
Performance | Cache Hit Latency | p95 <= 150 ms | Not verified | Partial | Needs performance test
Performance | Cache Miss Latency | p95 <= 900 ms | Not verified | Partial | Needs performance test
Scalability | Concurrent Cache Reads | Cache supports moderate concurrent access | Not confirmed | Partial | Important if cache implemented
Scalability | Thundering Herd Handling | Concurrent misses for same city should not overload provider | Not confirmed | Fail | BA edge case explicitly calls this out
Maintainability | Provider Adapter Modularity | Provider-specific mapping isolated from API contract | Not confirmed | Partial | Important future-change requirement
API Versioning | Endpoints under /api/v1 | Should be versioned | Partial | Need endpoint verification

## TEST CASES
Test ID | Category | Scenario | Precondition | Input | Expected Result | Priority | Notes
TC-HP-01 | Happy Path | Fetch weather by valid city on cache miss | No fresh cache exists for city | GET /api/v1/weather?city=London | 200 OK; requestId present; metadata.cacheHit=false; current weather returned; forecast returned; response uses canonical schema | High | Should also verify cache write occurs
TC-HP-02 | Happy Path | Fetch weather by valid city on fresh cache hit | Fresh cache exists for normalized city | GET /api/v1/weather?city=London | 200 OK; metadata.cacheHit=true; no provider call; response schema identical to cache-miss success | High | Validates cache reuse
TC-HP-03 | Happy Path | Fetch weather with mixed spaces/case | Input normalization supported | GET /api/v1/weather?city= nEw yOrK | 200 OK; city.normalized equals normalized form; deterministic cache key behavior; valid weather response | High | Tests BR-02 and EC-01
TC-HP-04 | Happy Path | Fetch weather with punctuation in city | Input validation supports punctuation | GET /api/v1/weather?city=St. John's | 200 OK or valid domain response; punctuation accepted by validation rules | Medium | EC-02
TC-HP-05 | Happy Path | Health endpoint | Check operational readiness | GET /api/v1/health | 200 OK with service status and provider connectivity snapshot | Medium | Operational requirement
TC-HP-06 | Happy Path | Metrics endpoint | Return counters | GET /api/v1/metrics | 200 OK with total requests, cache hits, cache misses, provider failures, validation failures | Medium | Internal endpoint
TC-EC-01 | Edge Case | Missing city parameter | None | GET /api/v1/weather | 400 VALIDATION_ERROR; standardized error schema with requestId, code, message, fieldErrors, timestampUtc | High | US-01
TC-EC-02 | Edge Case | City too short | None | GET /api/v1/weather?city=A | 400 VALIDATION_ERROR; fieldErrors includes city length issue | High | FR-01 validation
TC-EC-03 | Edge Case | City too long | None | GET /api/v1/weather?city=<101-char-string> | 400 VALIDATION_ERROR; fieldErrors includes city length issue | Medium | FR-01 validation
TC-EC-04 | Edge Case | Unsupported characters in city | None | GET /api/v1/weather?city=@@@### | 400 VALIDATION_ERROR; city rejected before provider/cache access | High | US-02
TC-EC-05 | Edge Case | Unknown but well-formed city | Provider returns unknown city | GET /api/v1/weather?city=Atlantis | 404 CITY_NOT_FOUND with standardized error schema | High | FR-07
TC-EC-06 | Edge Case | Provider returns fewer than 3 forecast days | Provider/mocked adapter returns 2 days | GET /api/v1/weather?city=TestCity | 200 OK; available forecast days returned; metadata.forecastCompleteness=partial | High | BR-09
TC-EC-07 | Edge Case | Provider payload missing optional wind/humidity | Optional fields absent from provider | GET /api/v1/weather?city=TestCity | 200 OK; schema-compliant response; optional fields null where applicable | Medium | US-04
TC-EC-08 | Edge Case | Duplicate or out-of-order forecast dates | Provider returns malformed forecast ordering | GET /api/v1/weather?city=TestCity | System normalizes ascending unique dates or rejects malformed payload safely; raw malformed provider payload not passed through | Medium | EC-10
TC-EC-09 | Edge Case | Cache entry expires during request processing | Near-expiry cached item exists | GET /api/v1/weather?city=London | Response is deterministic; no mixed freshness state; either valid cached or refreshed provider response | Low | EC-05
TC-EC-10 | Edge Case | Provider timeout with no cache | No cache and provider unavailable | GET /api/v1/weather?city=London | 503 DEPENDENCY_UNAVAILABLE with standardized error schema | High | EC-08
TC-EC-11 | Edge Case | Provider failure with stale fallback | Expired fresh cache but stale cache within 6 hours exists | GET /api/v1/weather?city=London | 200 OK; metadata.stale=true; fallbackSource=cache or equivalent; stale payload returned | High | US-03
TC-EC-12 | Edge Case | Provider failure with stale cache beyond tolerance | Only too-old stale cache exists | GET /api/v1/weather?city=London | 503 DEPENDENCY_UNAVAILABLE; stale cache not used | High | US-03
TC-ST-01 | Security | Injection-like city input | None | GET /api/v1/weather?city=Delhi;DROP TABLE | 400 validation error or safely treated as invalid input; no internal failure details leaked | High | Input sanitization
TC-ST-02 | Security | Script-like city input | None | GET /api/v1/weather?city=<script>alert(1)</script> | 400 validation error; no reflection of unsafe payload without escaping | High | Input sanitization
TC-ST-03 | Security | Error response secrecy | Trigger provider/internal failure | System-generated failure | Standardized error schema returned; no API keys, stack traces, provider secrets, or raw internal exceptions exposed | High | Security and reliability
TC-ST-04 | Security | Metrics endpoint internal access | If network restriction expected | GET /api/v1/metrics | Accessible only in intended environment or documented as internal-only | Medium | Operational security
TC-PT-01 | Performance | Cache hit latency | Fresh cache populated | Run repeated GET /api/v1/weather?city=London | p95 latency <= 150 ms | High | NFR-01
TC-PT-02 | Performance | Cache miss latency | No fresh cache populated | Run repeated GET /api/v1/weather?city=London | p95 latency <= 900 ms including provider call | High | NFR-01
TC-PT-03 | Performance | Concurrent requests same city on cache miss | Cache empty for target city | 20-50 parallel GET requests for same city | System avoids thundering herd; provider call count minimized; responses remain stable | High | EC-06
TC-PT-04 | Performance | Moderate request volume with cache enabled | System warmed with popular cities | Run sustained mixed request load | System remains stable; cache hit rate improves throughput; no excessive provider failure rate | Medium | NFR-07
TC-PT-05 | Performance | Provider timeout behavior | Timeout configured to 3 seconds | Trigger slow provider | Response fails fast near timeout threshold and follows retry/fallback policy | High | FR-06/NFR-04